## Action Plan
Technician Commitment Action Plan for the University of Cambridge 2024-27
| Updated 19-01-'24 |  |  | Phase 1 - 2024 |  |  |  | Phase 2 - 2025 |  |  |  | Phase 3 - 2026
Action number | Action | Who | Alignment with TALENT report recommendations | Jan-24 | Apr-24 | Jul-24 | Oct-24 | Jan-25 | Apr-25 | Jul-25 | Oct-25 | Jan-26 | Apr-26 | Jul-26 | Oct-26 | Status (RAG)
TALENT Commision Review Recommendations
1 | Secure funding for a Strategic Lead (R1) - This role could establish technical platforms, use data for horizon scanning and help facilitate progress of the TC Action Plan goals | University | R1, R5 | [12 empty] | Action needed - 1
2 | Active inclusion of technical staff representation on strategic decision-making boards (R12) | SL/DC/JN | R12 | [12 empty] | Action needed - 2
3 | Contribute to a job description review (at least for recruiting purposes going forwards) (R7, R8) | SL/JN | R7,R8 | [12 empty] | Action needed - 2
4 | Instigate a clear Career Pathway (including recommended entry routes/progression points) (R7, R9) | JN/OD | R7,R9 | [12 empty] | Action needed - 1
5 | Encourage culture change to engage technicians with their careers and training, including showcasing their work and the work of the University (R2, R15) | SL/JN/RC | R2,R15 | [12 empty] | Action needed - 2
6 | Provide University wide guidance on inclusion for accreditation using the Contributor Roles Taxonomy (CRediT) principles (R11) via Fair Acknowledgement Guidelines and associated Statement of Expectations including expanding the Vocational Training Budget | SL/LI/JN/RO | R11 | [12 empty] | Action needed - 2
7 | Secure funding to establish team to run comprehensive survey and resulting actions utilising the NTDC skills survey | University | R3 | [12 empty] | Ongoing/in progress
8 | Expand 'Research Culture training guidelines' to all technical staff/potentially all professional services staff | JN/RC | R10, R6 | [12 empty] | Action needed - 2
9 | Work with the new ITSS (Institute for Technical Skills and Strategy) to promote external training opportunities and collaborations | SL/JN | R13 | [12 empty] | Action needed - 2
no data | Overarching Actions
10 | Review and refine governance and scope of the Technician Commitment at Cambridge | LI/JN/DC | R12 | [12 empty] | Action needed - 1
11 | Seek resource to strengthen TC support team | LI | [13 empty] | Ongoing/in progress
12 | Review of line management arrangements for technicians and make recommendations to ensure involvement of technical/professional service managers in addition to academics. Inform the Strategic Workforce Programme and other OD programmes | LI/JN | R2,R7 | [12 empty] | Ongoing/in progress
13 | Identify initiatives to increase number of BAME technicians in the University such as the Tech Talent Charter and other national schemes | LI/JN | R4 | [12 empty] | Action needed - 2
14 | Research Culture - collaborate with colleagues on Research Culture and include technical staff in resulting interventions | JN/RC | R2 | [12 empty] | Action needed - 2
no data | Visibility
15 | Communicate the aims of the Technician Commitment widely across the University | JN | R15 | [12 empty] | Ongoing/in progress
16 | Continue to use Viva Engage, Teams channels and other forums to communicate with technicians and key stakeholders; continue to develop the Technician Commitment website as the 'go to' place for technicians to support their development, career progression, networking and access to resources | JN | R15 | [12 empty] | Ongoing/in progress
17 | Increase membership and participation of technical staff in decision-making committees and groups, to widen representation. | LI/JN/WG | R12 | [12 empty] | Action needed - 1
18 | Instigate outreach events and encourage support from technical staff to promote technical roles and develop staff skills | SL/JN | R3, R6, R7
1 | Recognition
19 | Run an ongoing poster campaign (including virtual) to recognise and promote the key contribution of technicians | JN | R6,R15 | [12 empty] | Ongoing/in progress
20 | Utilise University wide websites and the Technicians Make it Happen website, to promote the work of technicians and opportunities for technicians | SL/JN | R6, R15 | [12 empty] | Ongoing/in progress
21 | Support technicians with gaining professional registration status and raising awareness of this | JN | R10 | [12 empty] | Ongoing/in progress
22 | Publicise and encourage nominations of technicians for the annual Professional Services Recognition Scheme and external awards such as national awards eg THE, The Papin Prize and others | LI/JN | R11 | [12 empty] | Ongoing/in progress
no data | Career Development
23 | Deliver Technician Networking events regularly through the year | JN | R15 | [12 empty] | Ongoing/in progress
24 | Deliver a Technician Conference every 2 years (following the inaugural event in 2019) | JN | [13 empty] | Ongoing/in progress
25 | Maintain links with appropriate national bodies and their resources eg Higher Education and Technicians Education Development (HEaTED), National Technician Development Centre (NTDC) | LI/JN | R13 | [12 empty] | Ongoing/in progress
26 | Identify and promote best practice with regard to technician development and progression to departments | JN | [13 empty] | Ongoing/in progress
27 | Identify gaps in the training available for technicians; introduce new and updated training in response, which will also support Career Pathways work and Succession Planning | PPD/JN/OD | R1, R2, R3, R9, R10, R13 | [12 empty] | Action needed - 2
28 | Continue to encourage mentoring for technical staff and expand the uptake of the scheme. | PPD/JN | R10, R13, R15 | [12 empty] | Ongoing/in progress
Sustainability
29 | Support the West Cambridge Technician Apprenticeship Project and its roll-out to other sites | CL | R1 | [12 empty] | Ongoing/in progress
30 | Collate and publicise technician apprenticeship vacancies to increase visibility of technical roles available | CL | R1 | [12 empty] | Ongoing/in progress
31 | Increase outreach activities with local schools/colleges to promote technician careers and work experience, including Cambridge Academy for Science and Technology | CL/JN | R6 | [12 empty] | Action needed - 2
32 | Identify potential technician and skill shortage areas, following review of age, gender, race, grade and role profile data; highlight actions required | SL/JN/CL | R4, R1 | [12 empty] | Action needed - 2
33 | Continue to implement the 50% shared salary technician scheme | SL/CL | [13 empty] | Ongoing/in progress
no data | Evaluating Impact
34 | Establish evaluation criteria to measure success of the Technician Commitment at Cambridge eg turnover, promotions, skills shortages, take up of training and professional registration, success stories, anecdotal evidence. Tool not widely used | SL/JN | R3 | [12 empty] | Action needed - 2
35 | Complete annual evaluation report for relevant bodies eg Technician Agenda Steering Group, Personal and Professional Development Committee, include progress against metrics; lessons learnt, targets for future years | SL/LI/JN | R3 | [12 empty] | Action needed - 2
36 | Review and update action plan with input from TC Working Group, Technician Champion and technicians | LI/JN/WG | R3 | [12 empty] | Ongoing/in progress
Who
TCC: Technician Commitment Co-ordinator
CL: Colin Long, Apprenticeship Manager, PPD
WG: Technician Commitment Working Group
PPD: Personal and Professional Development team
DC: David Cardwell, Technician Champion and PVC
LI: Leonie Isaacson, Head of Learning and Development, PPD
JN: Technician Commitment Co-ordinator, PPD
CL: Colin Long, Apprenticeship Manager, PPD
WG: Technician Commitment Working Group
PPD: Personal and Professional Development team
SL: Strategic Lead post
OD: Organisational Development team
RC: Research Culture team
RO: Research Office
RAG
Action needed - priority 1
Action needed - priority 2
Ongoing/in progress
Action needed - priority 2
Ongoing/in progress
RAG (Additional Resourcing Requirements)*
High level of additional resourcing required
Medium level of additional resourcing required
Low level of additional resourcing required
*Resourcing costs could be time, expense and/or the need for wider University engagement/steering